## Sheet1
Hours
ES6 modules |  | 2
html + bootstrap |  | 7
file system issues |  | 3
front-end mechanism |  | 9
check feature | 2
uncheck feature | 1
display in template | 2
erase from template | 1
show scroll bar | 3
Jasmine integration |  | 5
XML parsing |  | 7
21 exercises |  | 21
XSD |  | 2
Function constructor (including validation) |  | 8
Page generation |  | 16
gather exercises | 4
gather features for active exercise | 4
hold focus on active exercise | 4
display empty review template | 4
Snippet lookup mechanism |  | 16
Feature to snippet map by exercise | 4
condition to feature map by exercise | 4
iterate through conditions | 4
match to category | 4
Inner HTML |  | 12
exercises | 4
features | 4
Review Template | 4
Review Template |  | 3
Copy to clipboard |  | 5
116